# Project Scope Document

Contoso International

# Project Overview

Implement Microsoft Dynamics 365 Business Central to streamline financial management, inventory control, and distribution processes for paper and boxing products at Contoso International.

# Objectives & Goals

Centralize financial and inventory data in Business Central.

Automate purchase and sales order processing.

Enable accurate stock level visibility across multiple warehouses.

Improve reporting for cost analysis and profitability.

# Deliverables

Configured Business Central environment (Finance, Inventory, Sales, Purchasing).

Data migration from legacy systems (customers, vendors, items, GL accounts).

User training and documentation.

Integration with existing logistics and shipping systems.

Go-live support and post-implementation review.

# In-Scope vs Out-of-Scope

| In-Scope | Out-of-Scope |
| --- | --- |
| Finance Module – General Ledger, Accounts Payable, Accounts Receivable, Bank Reconciliation, Fixed Assets | Advanced financial consolidation across multiple legal entities |
| Inventory Management – Item setup, stock levels, warehouse management, lot tracking | Advanced manufacturing (production orders, BOM management) |
| Sales & Purchasing – Sales Orders, Purchase Orders, Customer/Vendor setup, pricing, discounts | E-commerce integration or custom web portals |
| Warehouse Management – Bin setup, stock transfers, picking and shipping processes | Automated robotics or IoT warehouse integration |
| Reporting & Analytics – Standard financial reports, inventory valuation, sales performance dashboards | Custom Power BI dashboards beyond standard templates |
| Basic CRM – Customer contact management, interaction logs | Full CRM suite or marketing automation |
| Data Migration – Master data (customers, vendors, items), opening balances | Historical transactional data beyond agreed scope |
| User Training & UAT – Core modules only | Advanced training for non-core modules or third-party apps |

# Assumptions

Client provides clean and validated data for migration.

Users are available for training and UAT sessions.

Internet connectivity and hardware meet Business Central requirements.

# Constraints

Budget capped at ZAR 1,200,000.

Go-live deadline: June 30, 2026.

Limited internal IT resources for integration support.

# Acceptance Criteria

Successful migration of all master data and opening balances.

Users can process sales and purchase orders without errors.

Inventory valuation matches legacy system reports.

Financial statements generated accurately in Business Central.

# Stakeholder List

Project Sponsor: Operations Director

Project Manager: PM

Finance Lead: CFO

Warehouse Lead: Logistics Manager

IT Support: Internal IT Team

# High-Level Milestones

| Milestone | Target Date |
| --- | --- |
| Requirements gathering completed | Feb 15 |
| System configuration finalized | Mar 15 |
| Data migration completed | Apr 30 |
| UAT completed | May 15 |
| Go-live | June 30 |

# Risks & Mitigations

Risk: Data migration delays – Mitigation: Early data validation and mock migration

Risk: User resistance to new system – Mitigation: Comprehensive training and change management